## RISK REGISTER Worksheet
Worksheet RISK REGISTER
| RISK ANALYSIS | RISK ASSESSMENT |  |  | RISK CONTROL |  | RISK MONITORING
RISK IDENTIFICATION
No | RISK and description | Frequency/Probability | Impact/Severity | Priority | ACTION TAKEN | RESPONSIBLE PERSON | METHOD | TIMEFRAME | RESIDUAL RISK STATUS (E Effective N not effective)
1 | Patients tests are not performed due to increase in rejection of samples due to haemolysis | 4 | 4 | 16 | IA: Contact supplier to ensure adequate stock for coming month. Review inventory management process to identify problems in the process. Perform a RCA on identified problems. | Joe Soap | QI - Stock out | Monthly |  | Yes, no further monitoring required | 1 | 1
2 | Patients tests are not performed due to increase in rejection of samples due to haemolysis. | 3 | 2 | 6 |  | Mandisa K | QI - rejection rates | Monthly |  | Yes, continue to monitor | 2 | 2
3 | Potential incorrect patient results due to EQA reports not reviewed with in timeframe as set out in theprocedure. EQA results are accurate and no patient results affected | 3 | 1 | 3 |  | Joseph P | Supervisor review | Monthly |  | No, re evaluate actions | 3 | 3
4 | Potential impact on patient result TAT due to staffing having unplanned leave including sick leave | 3 | 2 | 6 |  | Joseph P | Staff record review | Monthly |  |  | 4 | 4
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on C3: Jan Scholtz: Based on Context - how many patients impacted, Accreditation impacted
Note on C5: 4 Frequent daily or 1 week 3 Occasonal 1 month 2 uncommon 1 years 1 Remote 2- 5 years
Note on D5: 4 Catastrophic 3 Major 2 Moderate 1 Minor